## Planificador de proyectos
Project Planning
[5 empty] | Week: | 34 |  |  | Plannign Duration | [6 empty] | Start Iteration |  |  |  |  | % Completed | [5 empty] | Real (out of planning) | [7 empty] | % Completed (out of planning)
Activity | Start of the Plan | Plannign Duration | Real Start | Real Duration | Completed | PERIODOS
[6 empty] | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Systems Requirements | 34 | 1 | 34 | 1 | 100%
Software Requirements | 35 | 1 | 35 | 1 | 75%
Git Set Up Repository | 36 | 0.25 | 36 | 0.25 | 100%
Risks Analysis | 37 | 0.25 | 38 | 0.25 | 100%
e2 Studio Installation | 39 | 2 | 39 | 2 | 100%
Configure GPI | 39 | 2 |  |  | 0%
Analog Input Config | 39 | 2 |  |  | 0%
PWM config | 39 | 2 |  |  | 0%
MCU clock config | 39 | 2 |  |  | 0%
SPI config | 39 | 2 |  |  | 0%
IRQ config | 39 | 2 |  |  | 0%
DC motor velocity control | 41 | 4 |  |  | 0%
Hall Effect Sensor config | 45 | 4 |  |  | 0%
Set Point resistor config | 49 | 2 |  |  | 0%
Shutdown | 51 | 2 |  |  | 0%
Set Point resistor config | 1 | 4 |  |  | 0%
LCD config | 5 | 4 |  |  | 0% | bar: PERIODOS 5 to PERIODOS 8
OS config | 9 | 4 |  |  | 0%
OS config | 13 | 4 |  |  | 0%
Diagnostics |  |  |  |  | 0%
Throughput analysis |  |  |  |  | 0%
Cyclomatic analysis complexity |  |  |  |  | 0%
Actividad 23 |  |  |  |  | 0%
Actividad 24 |  |  |  |  | 0%
Actividad 25 |  |  |  |  | 0%
Actividad 26 |  |  |  |  | 0%