## Sheet1
Iteration | Week | Date | SYS.2 Sistem Requirements Analysis | SWE.1 Sofware Requirements Analysis
1 | 36-37 | [03 - 14 Sep 2018] | DC Motor Velocity Control by means of a square signal whose pulse with varies trough time and presents a constant frequency fo = 10 KHz. | Configure the necessary pin for PWM signal generation with a fixed frequency of 10KHz.
2 | 38-39 | [17 - 28 Sep 2018] | Hall Efect Sensor coupled with motor rotor outputs 15 pulses per each 360° turn around. | Communication interface development to capture the Hall Efect Sensor pulses.
3 | 40-41 | [01 - 12 Oct 2018] | DC Motor Power Supply is 12 Volts. | GPIO Configuration to allow motor clockwise or anticlockwise rotation. (If necessary).
4 | 42-43 | [15 - 26 Oct 2018] | The reference value or "Set-Point" shoulg be defined by the use of a variable resistor. | Configure the necessary pin for Analog input voltage adquisition as well as ADC configuration for raw data reading.
5 | 44-45 | [29 - 09 Nov 2018] | The system should allow the user to set the Desired velocity by using the potentiometer. | Velocity Control Module Development.
6 | 46-47 | [12 - 23 Nov 2018] | The LCD Display or Graphical Interface must show the motor velocity and "Set-Point" (both in RPM's), as well as the PWM Duty Cycle percentage (%). | Human Machine Interface Development. "Project Name: DC Motor Velocity Control", "Duty cycle: XXX%", "Speed: XXXX RPM", "SW Version: X.X" "HW Version: CESEQ-C001/CESEQ-P001". Embedded Software Engineers: Last Name, Name.
7 | 48-49 | [26 - 07 Dec 2018] | OS configuration during boot-up | 1. EEPROM Memory 2. Timer by interruption avery XXms (User defined). 3. Watchdog timer.
8 | 50-51 | [10 - 21 Dec 2018] | The system should be able to detect: Battery and Earth short circuit | Diagnostics Module Development, Store values in EEPROM.
9 | 52-01 | [24 - 04 Jan 2019] | The system should keep track of Internal Memory corruption. | Diagnostics Module Development, Button in short circuit
10 | 02-03 | [07 - 18 Jan 2019] | Throghput Analysis and Tasks Management should be monitored in order to n. | Tasks could be monitored with a resolution of at least 10 TIC's. Furthermore, they should be stored in integer type variables. If the Throughput is greater than 70% the CPU use, Software design must be reconsidered. It will be necessary to divide states/tasks/subrutines in order to satify the desired Throughput.
11 | 04-05 | [21 - 01 Feb 2019] | Cyclomatic Complexity Analysis and Conventions and Standards. | Complexity through the CCCC, which must less than < 19.