## Planificador de proyectos
Project Planning
[5 empty] | Week: | 34 |  |  | Plannign Duration | [6 empty] | Start Iteration |  |  |  |  | % Completed | [5 empty] | Real (out of planning) | [7 empty] | % Completed (out of planning)
Activity | Start of the Plan | Plannign Duration | Real Start | Real Duration | Completed | PERIODOS
[6 empty] | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Systems Requirements | 34 | 1 | 34 | 1 | 100%
Software Requirements | 35 | 1 | 35 | 1 | 75%
Git Set Up Repository | 36 | 0.25 | 36 | 0.25 | 100%
Risks Analysis | 36 | 0.25 | 36 | 0.25 | 100%
Actividad 05 | 4 | 2 | 4 | 8 | 85%
Actividad 06 | 4 | 3 | 4 | 6 | 85%
Actividad 07 | 5 | 4 | 5 | 3 | 50%
Actividad 08 | 5 | 2 | 5 | 5 | 60%
Actividad 09 | 5 | 2 | 5 | 6 | 75%
Actividad 10 | 6 | 5 | 6 | 7 | 100%
Actividad 11 | 6 | 1 | 5 | 8 | 60%
Actividad 12 | 9 | 3 | 9 | 3 | 0%
Actividad 13 | 9 | 6 | 9 | 7 | 50%
Actividad 14 | 9 | 3 | 9 | 1 | 0%
Actividad 15 | 9 | 4 | 8 | 5 | 1%
Actividad 16 | 10 | 5 | 10 | 3 | 80%
Actividad 17 | 11 | 2 | 11 | 5 | 0%
Actividad 18 | 12 | 6 | 12 | 7 | 0%
Actividad 19 | 12 | 1 | 12 | 5 | 0%
Actividad 20 | 14 | 5 | 14 | 6 | 0%
Actividad 21 | 14 | 8 | 14 | 2 | 44%
Actividad 22 | 14 | 7 | 14 | 3 | 0%
Actividad 23 | 15 | 4 | 15 | 8 | 12%
Actividad 24 | 15 | 5 | 15 | 3 | 5%
Actividad 25 | 15 | 8 | 15 | 5 | 0%
Actividad 26 | 16 | 28 | 16 | 30 | 50%